## Summary
AfterShip Tracking: Test Summary
Updates on its own from the Status column of the Test Cases sheet.
Module | Total | Pass | Fail | Blocked | N/A | Not run | % executed | % pass
Settings | 11 | 11 | 0 | 0 | 0 | 0 | 100% | 100%
Courier list | 9 | 8 | 0 | 0 | 0 | 1 | 88.89% | 100%
Add shipment | 14 | 13 | 0 | 0 | 0 | 1 | 92.86% | 100%
Edit shipment | 4 | 3 | 0 | 0 | 0 | 1 | 75% | 100%
Customer emails | 8 | 8 | 0 | 0 | 0 | 0 | 100% | 100%
Webhook | 6 | 6 | 0 | 0 | 0 | 0 | 100% | 100%
Sync command | 4 | 4 | 0 | 0 | 0 | 0 | 100% | 100%
Staff alerts | 4 | 4 | 0 | 0 | 0 | 0 | 100% | 100%
Cancellation | 3 | 3 | 0 | 0 | 0 | 0 | 100% | 100%
Customer pages | 6 | 6 | 0 | 0 | 0 | 0 | 100% | 100%
Security | 3 | 3 | 0 | 0 | 0 | 0 | 100% | 100%
Error handling | 3 | 3 | 0 | 0 | 0 | 0 | 100% | 100%
Total | 75 | 72 | 0 | 0 | 0 | 3 | 96% | 100%
% pass = Pass / (Pass + Fail); Blocked and N/A are left out.
By priority
Priority | Total | Fail
Critical | 10 | 0
High | 32 | 0
Medium | 24 | 0
Low | 9 | 0

## Read me
How to use this file
What to fill in | Only the yellow columns on Test Cases: Status, Actual result, Tester, Date tested. Everything else describes the test.
Status values | Not run, Pass, Fail, Blocked, N/A (pick from the dropdown). The Summary sheet counts them.
Example of a filled row | Status = Fail ¦ Actual result = 'Customer received two shipped emails' ¦ Tester = JD ¦ Date tested = 2026-10-22
Automated test | The PHPUnit test that already covers the case (tests/Feature/AfterShipTrackingTest.php or tests/Isolated/AfterShipSettingsTest.php). 'Manual only' means no automated test, so check those by hand first.
Before you start
Test courier | Outside production, use courier 'testing-courier' with numbers like ITD-<minutes>-<6 to 16 digits>, e.g. ITD-1-123456789. AfterShip moves it through Label created > In transit > Delivered on its own.
API allowance | The AfterShip account is on the free plan: 100 API calls a day (resets 04:37 UTC). Each save, refresh, courier-list fetch and Test connection uses one; webhooks are free. A full manual run uses roughly 20 to 30 calls. Never poll in a loop.
Emails are real | The local .env sends real email through Brevo. Use test customers whose inboxes you own; never use real customers.
Queue worker | Order emails go through the queue. Start it (php artisan queue:work) or emails stay queued. php artisan mail:check shows the state.
Webhook tests | AfterShip can only reach a public URL, so webhook cases run on live or staging, or locally by POSTing a signed body (header aftership-hmac-sha256 = base64 HMAC-SHA256 of the raw body with the webhook secret).
Couriers | Only couriers activated in AfterShip > Settings > Couriers can be chosen. Activate An Post and DPD Ireland there before testing them.
Simulating failures | Bad key: save a wrong key in Settings > AfterShip, then restore it. Rate limits and outages are hard to cause by hand; the automated test for each is listed.

## Test Cases
TC ID | Module | Title | Preconditions | Steps | Test data | Expected result | Priority | Type | Status | Actual result | Tester | Date tested | Automated test
AS-SET-01 | Settings | AfterShip tab opens | Signed in as admin with Settings permission | 1. Go to Settings > AfterShip | - | Page shows API key, Webhook, Delivery and status checks, and Test connection sections. Webhook URL ends in /api/v1/aftership/webhook. | High | Positive | Pass | Automated: AfterShipSettingsTest::test_AS_SET_01_the_tab_gets_every_section_and_the_webhook_url (API side). Page layout not clicked through. | Automated (PHPUnit / node) | 2026-10-22 | AfterShipSettingsTest::test_AS_SET_01_the_tab_gets_every_section_and_the_webhook_url
AS-SET-02 | Settings | Save a new API key | No key saved in admin (state reads 'Not set' or 'From the server .env') | 1. Enter a valid API key 2. Click Save 3. Reload the page | Valid AfterShip API key | Saved. Field is empty after reload; state reads 'Set here, ending in <last 4>'. The full key is never shown. | High | Positive | Pass | Automated: AfterShipSettingsTest: a_saved_key_replaces_the_env_one passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipSettingsTest: a_saved_key_replaces_the_env_one
AS-SET-03 | Settings | Blank key keeps the saved one | A key is saved in admin | 1. Leave API key blank 2. Change another field (e.g. auto-deliver) 3. Save | - | Saved key is unchanged (same last 4 characters). | Medium | Positive | Pass | Automated: AfterShipSettingsTest: a_blank_key_keeps_the_saved_one passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipSettingsTest: a_blank_key_keeps_the_saved_one
AS-SET-04 | Settings | Switch back to the .env value | A key is saved in admin | 1. Click 'Use the server .env value instead' 2. Save | - | Before save the state reads 'Will switch back to the server .env value when you save'. After save it reads 'From the server .env, ending in ...' (or 'Not set'). | Medium | Positive | Pass | Automated: AfterShipSettingsTest: clear_goes_back_to_env passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipSettingsTest: clear_goes_back_to_env
AS-SET-05 | Settings | Secrets never returned by the API | A key and webhook secret are saved | 1. Open browser DevTools > Network 2. Load Settings > AfterShip 3. Inspect the response of GET /api/admin/setting/aftership | - | Response has only set / source / last 4 for each secret. No full key or secret anywhere. | High | Security | Pass | Automated: AfterShipSettingsTest: the_page_never_returns_a_secret passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipSettingsTest: the_page_never_returns_a_secret
AS-SET-06 | Settings | Test connection with a good key | Valid key saved | 1. Click Test connection | - | Shows 'Connected. N couriers are activated:' and lists them. Uses 1 API call. | High | Positive | Pass | Automated: AfterShipSettingsTest: test_connection_lists_the_activated_couriers passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipSettingsTest: test_connection_lists_the_activated_couriers
AS-SET-07 | Settings | Test connection with a bad key | Save an invalid key (e.g. change one character) | 1. Click Test connection | Invalid key | A clear refusal message is shown, even if an old courier list is stored. Restore the good key afterwards. | High | Negative | Pass | Automated: AfterShipSettingsTest: test_connection_reports_a_rejected_key passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipSettingsTest: test_connection_reports_a_rejected_key
AS-SET-08 | Settings | Sync interval limits | - | 1. Enter 10 in 'Check each parcel every', Save 2. Enter 2000, Save 3. Enter 60, Save 4. Clear the field, Save | 10, 2000, 60, blank | 10 and 2000 are refused: 'Enter a whole number of minutes between 15 and 1440, or leave it blank for automatic.' 60 saves. Blank saves and shows 'Automatic (...)' (12 h with a webhook secret, 1 h without). | Medium | Boundary | Pass | Automated: AfterShipSettingsTest: a_check_interval_outside_the_limits_is_refused passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipSettingsTest: a_check_interval_outside_the_limits_is_refused
AS-SET-09 | Settings | Auto-deliver switched off | Order On the way with a tracking | 1. Turn off 'Mark the order Delivered when the courier delivers it', Save 2. Courier reports Delivered (webhook or sync) | - | Shipment shows Delivered, but the order stays On the way. Turn the switch back on afterwards. | Medium | Positive | Pass | Automated: AfterShipSettingsTest: the_delivered_scan_can_be_switched_off passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipSettingsTest: the_delivered_scan_can_be_switched_off
AS-SET-10 | Settings | Admin without Settings permission | Admin role without Settings permission | 1. Try to save Settings > AfterShip (or POST /api/admin/setting/aftership) | - | Save is refused. Nothing changes. | High | Security | Pass | Automated: AfterShipSettingsTest: an_admin_without_settings_permission_cannot_save passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipSettingsTest: an_admin_without_settings_permission_cannot_save
AS-SET-11 | Settings | New key drops the old courier list | Key A saved, courier list loaded | 1. Save key B (a different AfterShip account) 2. Open an order's courier picker | Key B | Courier list shows account B's activated couriers, not account A's. | Medium | Positive | Pass | Automated: AfterShipSettingsTest: a_new_key_drops_the_old_accounts_courier_list passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipSettingsTest: a_new_key_drops_the_old_accounts_courier_list
AS-COU-01 | Courier list | Only activated couriers offered | Couriers activated in AfterShip > Settings > Couriers | 1. Open a Confirmed order 2. Click 'Search your AfterShip couriers' under Shipment tracking | - | Only couriers activated in the AfterShip account appear (plus testing-courier outside production). | High | Positive | Pass | Automated: AfterShipTrackingTest: only_couriers_activated_in_aftership_are_offered passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: only_couriers_activated_in_aftership_are_offered
AS-COU-02 | Courier list | Search the courier list | Courier list loaded | 1. Type part of a courier name 2. Type a word that matches nothing | 'fed', 'zzzz' | List filters to matching couriers. No match shows the 'no match' note. | Low | Positive | Not run | UI only. Filter logic read in admin-panel/pages/orders/_id.vue (courierOptions matches name, other name, slug; no-match note) and looks right. Click through once on staging. |  |  | Manual only
AS-COU-03 | Courier list | Refresh courier list | A courier was just activated in AfterShip | 1. Click 'Refresh courier list' | - | The newly activated courier appears. | Medium | Positive | Pass | Automated: AfterShipTrackingTest::test_the_courier_list_is_fetched_from_aftership_then_served_from_the_stored_copy (refresh=1 re-reads AfterShip). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest::test_the_courier_list_is_fetched_from_aftership_then_served_from_the_stored_copy
AS-COU-04 | Courier list | Courier not activated is refused | A courier slug that is not activated in the account | 1. Send POST /api/admin/order/shipment with that slug (DevTools or Postman) | courier = an inactive slug | Refused on the Courier field: 'That courier is not activated in your AfterShip account...'. No AfterShip call made. | High | Negative | Pass | Automated: AfterShipTrackingTest: a_courier_aftership_lists_but_the_account_has_not_activated_is_refused passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: a_courier_aftership_lists_but_the_account_has_not_activated_is_refused
AS-COU-05 | Courier list | Courier list when AfterShip is down | List fetched once before; then AfterShip blocked (bad key or no network) | 1. Open the courier picker | - | The stored list is still shown. With no stored list, a clear error appears instead. | Medium | Negative | Pass | Automated: AfterShipTrackingTest: a_stale_copy_is_used_when_aftership_is_down passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: a_stale_copy_is_used_when_aftership_is_down
AS-COU-06 | Courier list | Test courier hidden in production | APP_ENV=production | 1. Open the courier picker 2. Try to save testing-courier through the API | - | testing-courier is not listed, and saving it is refused. | Medium | Negative | Pass | Automated: AfterShipTrackingTest: the_test_courier_is_hidden_and_refused_where_not_allowed passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: the_test_courier_is_hidden_and_refused_where_not_allowed
AS-COU-07 | Courier list | Courier needing a postcode | A courier whose required fields include a postcode; order address has one | 1. Pick that courier 2. Save a tracking number | - | A note shows the fields filled from the order. Save succeeds. | Medium | Positive | Pass | Automated: AfterShipTrackingTest: a_courier_needing_a_postcode_gets_it_from_the_order passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: a_courier_needing_a_postcode_gets_it_from_the_order
AS-COU-08 | Courier list | Courier needing a postcode, order has none | Same courier; order address has no postcode | 1. Pick the courier 2. Save | - | Refused: '<Courier> also needs: ...'. Nothing saved. | Medium | Negative | Pass | Automated: AfterShipTrackingTest: a_courier_needing_a_postcode_is_refused_when_the_order_has_none passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: a_courier_needing_a_postcode_is_refused_when_the_order_has_none
AS-COU-09 | Courier list | Courier needing account number or key | A courier that needs an account number or tracking key | 1. Pick the courier 2. Leave the extra field empty, Save 3. Enter a value with a symbol, Save 4. Enter a valid value, Save | 'ABC#1', then 'ABC123' | Empty: '<Courier> also needs: ...'. Symbol: 'The courier account number is letters and digits only.' Valid value saves. | Medium | Negative | Pass | Automated: AfterShipTrackingTest: account_number_and_key_are_asked_of_the_admin passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: account_number_and_key_are_asked_of_the_admin
AS-SHP-01 | Add shipment | Add tracking to a Confirmed order | Order Confirmed, home delivery, customer email is a test inbox you own | 1. Open the order 2. Pick a courier 3. Enter the tracking number 4. Click 'Save & notify customer' | testing-courier, ITD-1-123456789 | Shipment shows courier, number and 'Awaiting courier scan'. Order moves to On the way. Customer gets ONE shipped email with courier, number and a 'Track your parcel' button. | Critical | Positive | Pass | Automated: AfterShipTrackingTest: saving_a_shipment_registers_it_ships_the_order_and_emails_the_link_once passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: saving_a_shipment_registers_it_ships_the_order_and_emails_the_link_once
AS-SHP-02 | Add shipment | Add tracking to a Picked up order | Order Picked up | Same steps as above | testing-courier, ITD-2-223456789 | Same result as for a Confirmed order. | High | Positive | Pass | Automated: AfterShipTrackingTest::test_AS_SHP_02_a_picked_up_order_ships_like_a_confirmed_one | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest::test_AS_SHP_02_a_picked_up_order_ships_like_a_confirmed_one
AS-SHP-03 | Add shipment | Add tracking to an order already On the way | Order already On the way, no shipment yet | 1. Add courier + number 2. Save | - | Customer gets ONE 'tracking added' email, not the shipped email again. Order status unchanged. | High | Positive | Pass | Automated: AfterShipTrackingTest: an_order_already_on_its_way_gets_one_tracking_email passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: an_order_already_on_its_way_gets_one_tracking_email
AS-SHP-04 | Add shipment | Double click / same details again | A shipment was just saved | 1. Save the exact same courier + number again (or double click Save) | - | No second AfterShip call, no second email, no error. A save made while the first is still running is refused: 'This shipment is already being saved. Wait a moment, then reload the order.' | Critical | Negative | Pass | Automated: AfterShipTrackingTest: resubmitting_the_same_shipment / a_second_save_while_the_first_is_running_is_refused passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: resubmitting_the_same_shipment / a_second_save_while_the_first_is_running_is_refused
AS-SHP-05 | Add shipment | Number with spaces and lower case | - | 1. Enter the number with spaces and lower-case letters 2. Save | 'itd 1 123456789' | Saved in upper case with the spaces removed. Re-saving the spaced version counts as the same number. | Medium | Positive | Pass | Automated: AfterShipTrackingTest::test_AS_SHP_05_a_spaced_lower_case_number_is_stored_normalised_and_counts_as_the_same | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest::test_AS_SHP_05_a_spaced_lower_case_number_is_stored_normalised_and_counts_as_the_same
AS-SHP-06 | Add shipment | Invalid tracking number format | - | Enter each value and Save | 'ab1' (too short), 'ABCDEFG' (no digit), 'AB--12', 'AB_12#', 65+ characters | Each one refused, e.g. 'Enter the tracking number as printed on the label: letters and digits, at least one digit, single dashes or spaces between groups.' No AfterShip call. | High | Negative | Pass | Automated: AfterShipTrackingTest: malformed_tracking_numbers_are_refused_before_aftership_is_called passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: malformed_tracking_numbers_are_refused_before_aftership_is_called
AS-SHP-07 | Add shipment | No courier chosen | - | 1. Enter a number, leave the courier empty 2. Save | - | Refused: 'Choose a courier from the list.' | Medium | Negative | Pass | Automated: AfterShipTrackingTest: a_courier_outside_the_list_is_refused passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: a_courier_outside_the_list_is_refused
AS-SHP-08 | Add shipment | Number AfterShip rejects | - | 1. Save a number in the wrong format for the chosen courier | - | AfterShip's reason shown on the tracking number field. Nothing saved, order status unchanged, no email. | High | Negative | Pass | Automated: AfterShipTrackingTest: a_number_aftership_rejects_shows_its_reason_and_saves_nothing passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: a_number_aftership_rejects_shows_its_reason_and_saves_nothing
AS-SHP-09 | Add shipment | Pending order refused | Order Pending | 1. Try to add a shipment | - | Refused: 'Only a confirmed, picked up or on-the-way order can be given a shipment. Confirm the order first.' | High | Negative | Pass | Automated: AfterShipTrackingTest: pending_or_finished_orders_cannot_be_given_a_shipment passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: pending_or_finished_orders_cannot_be_given_a_shipment
AS-SHP-10 | Add shipment | Closed orders refused | Orders that are Delivered, Cancelled, Returned and Refunded | 1. Try to add a shipment to each | - | Each refused with the same message. No email. | High | Negative | Pass | Automated: AfterShipTrackingTest: pending_or_finished_orders_cannot_be_given_a_shipment passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: pending_or_finished_orders_cannot_be_given_a_shipment
AS-SHP-11 | Add shipment | Click & Collect order refused | Order with Click & Collect shipping | 1. Try to add a shipment | - | Refused: 'This is a Click & Collect order; there is no parcel to track.' | High | Negative | Pass | Automated: AfterShipTrackingTest::test_AS_SHP_11_a_click_and_collect_order_is_refused | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest::test_AS_SHP_11_a_click_and_collect_order_is_refused
AS-SHP-12 | Add shipment | Tracking AfterShip already holds | The courier + number already exists in AfterShip (e.g. added there by hand) | 1. Save that courier + number on the order | - | The existing AfterShip tracking is adopted, not duplicated. If it is already Delivered there, the order moves to Delivered. | Medium | Positive | Pass | Automated: AfterShipTrackingTest: a_tracking_aftership_already_holds_is_adopted_not_duplicated passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: a_tracking_aftership_already_holds_is_adopted_not_duplicated
AS-SHP-13 | Add shipment | Copy number and open tracking | Shipment saved | 1. Click copy next to the number 2. Click 'Open tracking page' | - | Number copied to the clipboard. The courier's tracking page opens in a new tab. | Low | UI | Not run | UI only (clipboard, new tab). Code read: copies tracking_number, link opens external_url with target=_blank. Click through once on staging. |  |  | Manual only
AS-SHP-14 | Add shipment | Admin refresh | Shipment saved | 1. Click Refresh on the shipment | - | Status re-read from AfterShip; 'last checked' time updates. On failure the error is shown on the shipment. | Medium | Positive | Pass | Automated: AfterShipTrackingTest: admin_refresh_reads_aftership_and_records_a_failure_on_the_row passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: admin_refresh_reads_aftership_and_records_a_failure_on_the_row
AS-EDT-01 | Edit shipment | Correct the tracking number | Shipment saved, customer already emailed | 1. Click Edit 2. Enter a different number 3. Save | testing-courier, ITD-1-987654321 | Shipment shows the new number. Customer is NOT emailed again; their existing link shows the new details. Old tracking removed from AfterShip. | High | Positive | Pass | Automated: AfterShipTrackingTest: correcting_a_shipment_never_emails_the_customer_again / a_corrected_number_removes_the_old_tracking passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: correcting_a_shipment_never_emails_the_customer_again / a_corrected_number_removes_the_old_tracking
AS-EDT-02 | Edit shipment | Correct the courier | Shipment saved | 1. Click Edit 2. Choose a different courier, same number 3. Save | - | Saved with the new courier. No new customer email. | Medium | Positive | Pass | Automated: AfterShipTrackingTest::test_AS_EDT_02_changing_only_the_courier_saves_it_and_emails_nobody | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest::test_AS_EDT_02_changing_only_the_courier_saves_it_and_emails_nobody
AS-EDT-03 | Edit shipment | Old number shared with another order | Two orders use the same courier + number | 1. Correct the number on one of them | - | The other order keeps its tracking; the old tracking is NOT deleted from AfterShip. | Low | Edge | Pass | Automated: AfterShipTrackingTest: a_corrected_number_removes_the_old_tracking_unless_another_order_shares_it passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: a_corrected_number_removes_the_old_tracking_unless_another_order_shares_it
AS-EDT-04 | Edit shipment | Cancel the edit | Shipment saved | 1. Click Edit 2. Change the fields 3. Click Cancel | - | The form closes; the saved shipment is unchanged. | Low | UI | Not run | UI only. Code read: cancelShipmentEdit closes the form and resets it to the saved shipment. Click through once on staging. |  |  | Manual only
AS-EML-01 | Customer emails | Shipped email content | Shipment just saved on a Confirmed order | 1. Open the email in the test inbox 2. Click 'Track your parcel' | - | Email shows courier name and tracking number. The button opens /track-order with the signed link and shows the full parcel. | Critical | Positive | Pass | Automated: AfterShipTrackingTest::test_AS_EML_01_the_track_button_opens_the_full_parcel (follows the email button href to /track-order). Real inbox not checked. | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest::test_AS_EML_01_the_track_button_opens_the_full_parcel
AS-EML-02 | Customer emails | Out for delivery email | Order On the way | 1. Courier reports OutForDelivery (webhook or sync) 2. Send the same status again | - | Customer gets ONE 'out for delivery' email. The repeat sends nothing. | High | Positive | Pass | Automated: AfterShipTrackingTest: out_for_delivery_and_a_failed_attempt_each_email_the_customer_once passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: out_for_delivery_and_a_failed_attempt_each_email_the_customer_once
AS-EML-03 | Customer emails | Delivery attempt failed email | Order On the way | 1. Courier reports AttemptFail | - | Customer gets ONE 'delivery attempt failed' email. A staff alert is sent too. | High | Positive | Pass | Automated: AfterShipTrackingTest: out_for_delivery_and_a_failed_attempt_each_email_the_customer_once passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: out_for_delivery_and_a_failed_attempt_each_email_the_customer_once
AS-EML-04 | Customer emails | Ready for pickup email | Order On the way | 1. Courier reports AvailableForPickup | - | Customer gets ONE 'ready for pickup' email. | Medium | Positive | Pass | Automated: AfterShipTrackingTest: ready_for_pickup_emails_the_customer_once passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: ready_for_pickup_emails_the_customer_once
AS-EML-05 | Customer emails | Delivered by the courier | Auto-deliver ON, order On the way | 1. Courier reports Delivered 2. Send Delivered again | - | Order moves to Delivered once (changed by 'aftership') with the usual delivered email, loyalty points and cash-on-delivery paid stamp. The repeat changes nothing. | Critical | Positive | Pass | Automated: AfterShipTrackingTest: webhook_updates_status_keeps_only_town_level_places_and_delivers_the_order_once passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: webhook_updates_status_keeps_only_town_level_places_and_delivers_the_order_once
AS-EML-06 | Customer emails | No emails for a closed order | Order Cancelled after its shipment was saved | 1. Courier reports OutForDelivery, then AttemptFail | - | No customer email and no staff alert. | High | Negative | Pass | Automated: AfterShipTrackingTest: no_alerts_or_customer_emails_for_a_cancelled_order passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: no_alerts_or_customer_emails_for_a_cancelled_order
AS-EML-07 | Customer emails | AfterShip sends no emails of its own | Shipment saved | 1. Check the customer inbox for mail from AfterShip | - | No AfterShip-branded emails arrive. | High | Negative | Pass | Automated: AfterShipTrackingTest::test_AS_EML_07_nothing_that_lets_aftership_contact_the_customer_is_sent (no emails/smses/customers/name/phone sent to AfterShip). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest::test_AS_EML_07_nothing_that_lets_aftership_contact_the_customer_is_sent
AS-EML-08 | Customer emails | Emails need the queue worker | Queue worker stopped | 1. Save a shipment 2. Run php artisan mail:check 3. Start the queue worker | - | The email waits in the queue and mail:check flags the stalled worker. Once the worker starts, the email is sent. | Medium | Edge | Pass | Automated: AfterShipTrackingTest::test_AS_EML_08_with_a_real_queue_the_email_waits_for_the_worker (database queue: queued, then sent by queue:work). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest::test_AS_EML_08_with_a_real_queue_the_email_waits_for_the_worker
AS-WHK-01 | Webhook | Webhook with no secret configured | No webhook secret saved, none in .env | 1. POST any body to /api/v1/aftership/webhook | - | HTTP 503, {"received": false}. | High | Negative | Pass | Automated: AfterShipTrackingTest: webhook_refuses_unsigned_badly_signed_and_unconfigured_calls passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: webhook_refuses_unsigned_badly_signed_and_unconfigured_calls
AS-WHK-02 | Webhook | Missing or bad signature | Webhook secret set | 1. POST without the aftership-hmac-sha256 header 2. POST with a wrong header value | - | HTTP 401, {"received": false}. Warning logged. Nothing updated. | Critical | Security | Pass | Automated: AfterShipTrackingTest: webhook_refuses_unsigned_badly_signed_and_unconfigured_calls passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: webhook_refuses_unsigned_badly_signed_and_unconfigured_calls
AS-WHK-03 | Webhook | Valid webhook updates the shipment | Secret set here and the URL added in AfterShip > Settings > Webhooks | 1. Save a test-courier shipment 2. Wait for it to move InfoReceived > InTransit > Delivered | testing-courier, ITD-<mins>-<6-16 digits> | HTTP 200, {"received": true, "updated": 1} for each. The admin screen shows each status. Places are town-level only. | Critical | Positive | Pass | Automated: AfterShipTrackingTest: webhook_updates_status_keeps_only_town_level_places_and_delivers_the_order_once passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: webhook_updates_status_keeps_only_town_level_places_and_delivers_the_order_once
AS-WHK-04 | Webhook | Tracking not on any order | - | 1. Send a correctly signed webhook for a number on no order | - | HTTP 200, {"received": true, "updated": 0}. Nothing changes. | Medium | Edge | Pass | Automated: AfterShipTrackingTest: webhook_for_a_tracking_we_do_not_hold_is_acknowledged_and_ignored passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: webhook_for_a_tracking_we_do_not_hold_is_acknowledged_and_ignored
AS-WHK-05 | Webhook | Older update arrives late | Shipment at In transit | 1. Replay an older (InfoReceived) signed webhook | - | Status stays In transit. | Medium | Edge | Pass | Automated: AfterShipTrackingTest: an_older_webhook_never_overwrites_a_newer_status passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: an_older_webhook_never_overwrites_a_newer_status
AS-WHK-06 | Webhook | Delivered after cancel | Order Cancelled | 1. Send a Delivered webhook for its tracking | - | Order stays Cancelled. | High | Negative | Pass | Automated: AfterShipTrackingTest: delivered_scan_never_revives_a_cancelled_order passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: delivered_scan_never_revives_a_cancelled_order
AS-SYN-01 | Sync command | Sync refreshes stale shipments | Shipments in flight, last checked longer ago than the interval | 1. Run php artisan aftership:sync | - | Stale shipments updated from AfterShip. Delivered, returned and refunded orders skipped. | High | Positive | Pass | Automated: AfterShipTrackingTest: sync_command_refreshes_stale_in_flight_shipments_from_aftership passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: sync_command_refreshes_stale_in_flight_shipments_from_aftership
AS-SYN-02 | Sync command | Interval follows the webhook | Sync interval left blank (automatic) | 1. Run sync with a webhook secret set 2. Run sync with none | - | With a secret, each shipment is checked every 12 h. Without one, every 1 h. | Medium | Positive | Pass | Automated: AfterShipTrackingTest: the_sync_checks_every_12h_with_a_webhook_and_hourly_without passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: the_sync_checks_every_12h_with_a_webhook_and_hourly_without
AS-SYN-03 | Sync command | Daily API allowance used up | AfterShip answers with its daily-limit 429 | 1. Save a shipment 2. Run sync | - | Reported as the daily allowance being used up (not 'AfterShip unreachable'). Not retried; sync stops. | Medium | Negative | Pass | Automated: AfterShipTrackingTest: a_spent_daily_allowance_is_reported_as_such_and_not_retried passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: a_spent_daily_allowance_is_reported_as_such_and_not_retried
AS-SYN-04 | Sync command | Short rate limit retried once | AfterShip answers one short 429 | 1. Save a shipment | - | Retried once and saved. If the limit persists, a clear message is shown and nothing is saved. | Low | Negative | Pass | Automated: AfterShipTrackingTest: a_rate_limited_create_is_retried_once_then_succeeds passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: a_rate_limited_create_is_retried_once_then_succeeds
AS-ALR-01 | Staff alerts | No scan 48 hours after entry | Tracking entered 48+ h ago, still Awaiting courier scan | 1. Run php artisan aftership:sync 2. Run it again | - | ONE email to the support address and a warning on the admin order screen. The second run sends nothing. | High | Positive | Pass | Automated: AfterShipTrackingTest: a_parcel_with_no_courier_scan_after_48_hours_alerts_staff_once passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: a_parcel_with_no_courier_scan_after_48_hours_alerts_staff_once
AS-ALR-02 | Staff alerts | AttemptFail, Exception, Expired | Order On the way | 1. Courier reports each status in turn | - | ONE staff email per reason, and the matching warning on the order screen. | High | Positive | Pass | Automated: AfterShipTrackingTest: a_failed_attempt_and_an_exception_alert_staff_once_each passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: a_failed_attempt_and_an_exception_alert_staff_once_each
AS-ALR-03 | Staff alerts | Wrong or unrecognised courier | A number saved under the wrong courier | 1. AfterShip reports Pending_004, Pending_006 or Pending_002 | - | Alert raised at once, with no 48 h wait, e.g. 'AfterShip says this tracking number does not belong to the selected courier...'. | Medium | Negative | Pass | Automated: AfterShipTrackingTest: a_wrong_or_unrecognised_courier_is_flagged_and_alerted_at_once passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: a_wrong_or_unrecognised_courier_is_flagged_and_alerted_at_once
AS-ALR-04 | Staff alerts | Order delivered by hand | Staff set the order to Delivered; no courier scan | 1. Run sync 48+ h after the number was entered | - | No 'no scan' alert or warning. | Low | Edge | Pass | Automated: AfterShipTrackingTest: no_scan_is_neither_alerted_nor_shown_for_an_order_delivered_by_hand passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: no_scan_is_neither_alerted_nor_shown_for_an_order_delivered_by_hand
AS-CAN-01 | Cancellation | Cancel before the courier scan | Shipment at Awaiting courier scan or Label created | 1. Cancel the order | - | Tracking removed from AfterShip. Shipment note: 'Order cancelled before the courier scanned the parcel; tracking removed from AfterShip.' | High | Positive | Pass | Automated: AfterShipTrackingTest: cancelling_before_the_courier_scan_removes_the_tracking_from_aftership passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: cancelling_before_the_courier_scan_removes_the_tracking_from_aftership
AS-CAN-02 | Cancellation | Cancel after a scan | Shipment In transit | 1. Cancel the order | - | Tracking kept in AfterShip so the return can be followed. | Medium | Positive | Pass | Automated: AfterShipTrackingTest: cancelling_after_a_scan_keeps_tracking_so_the_return_can_be_followed passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: cancelling_after_a_scan_keeps_tracking_so_the_return_can_be_followed
AS-CAN-03 | Cancellation | Cancel while AfterShip is down | AfterShip unreachable | 1. Cancel the order | - | Cancellation succeeds anyway. | High | Negative | Pass | Automated: AfterShipTrackingTest: aftership_being_down_never_blocks_a_cancellation passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: aftership_being_down_never_blocks_a_cancellation
AS-CUS-01 | Customer pages | Track order with the emailed link | Shipped email received | 1. Click 'Track your parcel' | - | /track-order shows courier, status, the full tracking number and the scan history. | Critical | Positive | Pass | Automated: AfterShipTrackingTest: public_tracking_shows_courier_and_status_but_the_number_and_trail_need_the_signed_link passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: public_tracking_shows_courier_and_status_but_the_number_and_trail_need_the_signed_link
AS-CUS-02 | Customer pages | Track order without the signed link | Signed out | 1. Open /track-order and look the order up without the t parameter | - | Courier and status only. Tracking number masked, no scan history, no prices. | Critical | Security | Pass | Automated: AfterShipTrackingTest: public_tracking_shows_courier_and_status_but_the_number_and_trail_need_the_signed_link passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: public_tracking_shows_courier_and_status_but_the_number_and_trail_need_the_signed_link
AS-CUS-03 | Customer pages | Tampered link | - | 1. Change one character of t in the emailed link | - | Treated as unsigned: number masked, no history. | High | Security | Pass | Automated: AfterShipTrackingTest::test_AS_CUS_03_a_link_with_one_character_changed_is_treated_as_unsigned | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest::test_AS_CUS_03_a_link_with_one_character_changed_is_treated_as_unsigned
AS-CUS-04 | Customer pages | My order page shows the parcel | Signed in as the order's owner | 1. Account > My orders > open the order | - | Parcel shows courier, number, status and history. | High | Positive | Pass | Automated: AfterShipTrackingTest: my_order_page_gets_the_full_parcel_for_its_owner_only passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: my_order_page_gets_the_full_parcel_for_its_owner_only
AS-CUS-05 | Customer pages | Another customer's order | Signed in as a different customer | 1. Open the first customer's order URL | - | Parcel details not shown. | High | Security | Pass | Automated: AfterShipTrackingTest: my_order_page_gets_the_full_parcel_for_its_owner_only passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: my_order_page_gets_the_full_parcel_for_its_owner_only
AS-CUS-06 | Customer pages | Status labels | Shipments in each status | 1. View the customer page for each status | - | Labels: Awaiting courier scan, Label created, In transit, Out for delivery, Delivery attempt failed, Delivered, Ready for pickup, Delivery problem, No recent updates. A message that repeats the status is not shown twice. | Low | UI | Pass | Automated: AfterShipTrackingTest: a_status_message_that_repeats_the_status_is_not_shown_twice passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: a_status_message_that_repeats_the_status_is_not_shown_twice
AS-SEC-01 | Security | Shipment endpoints need an admin | Signed out, or signed in as a customer | 1. Call POST /api/admin/order/shipment, POST shipment-refresh/{id} and GET shipment-couriers | - | All refused. | Critical | Security | Pass | Automated: AfterShipTrackingTest: the_shipment_endpoints_need_an_admin / the_courier_endpoints_need_an_admin passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: the_shipment_endpoints_need_an_admin / the_courier_endpoints_need_an_admin
AS-SEC-02 | Security | API key never sent to the browser | Admin order screen open | 1. Inspect the order and courier responses in DevTools | - | No AfterShip API key or webhook secret in any response. | Critical | Security | Pass | Automated: AfterShipTrackingTest: admin_order_screen_gets_the_shipment_and_courier_list_but_never_the_key passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: admin_order_screen_gets_the_shipment_and_courier_list_but_never_the_key
AS-SEC-03 | Security | No private data sent to AfterShip | Shipment saved | 1. Open the tracking in the AfterShip dashboard | - | Town-level destination and origin only. No customer name, email, phone or Eircode. | High | Security | Pass | Automated: AfterShipTrackingTest: town_level_destination_and_origin_are_sent_but_never_the_eircode_or_personal_details passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: town_level_destination_and_origin_are_sent_but_never_the_eircode_or_personal_details
AS-ERR-01 | Error handling | Bad key, outage, unreachable | A bad key saved, or the network blocked | 1. Save a shipment | - | A plain message on the Courier field (key refused / AfterShip down / unreachable). Nothing saved, no email. | High | Negative | Pass | Automated: AfterShipTrackingTest: unsupported_courier_bad_key_outage_and_unreachable_are_reported_plainly passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: unsupported_courier_bad_key_outage_and_unreachable_are_reported_plainly
AS-ERR-02 | Error handling | Order cancelled during the save | Two admins: one saves the shipment while the other cancels the order | 1. Save and cancel at the same moment | - | 'The order was closed while the shipment was being saved, so the customer was not told. Reload the order.' Tracking removed. | Low | Edge | Pass | Automated: AfterShipTrackingTest: an_order_cancelled_while_aftership_is_called_is_not_told_and_its_tracking_is_removed passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: an_order_cancelled_while_aftership_is_called_is_not_told_and_its_tracking_is_removed
AS-ERR-03 | Error handling | Half-finished save | A save stored the shipment but failed before moving the order | 1. Click Save again | - | The retry finishes the job: order moves to On the way, one email sent. | Low | Edge | Pass | Automated: AfterShipTrackingTest: a_save_that_stored_the_row_but_did_not_ship_the_order_is_finished_by_the_retry passed (AfterShip API faked; no live calls). | Automated (PHPUnit / node) | 2026-10-22 | AfterShipTrackingTest: a_save_that_stored_the_row_but_did_not_ship_the_order_is_finished_by_the_retry